## Slide 1: Project Meridian
Skyway 4.0 Platform Migration - Monthly Status Report
Reporting period: 1-31 July 2026 | PMO: Dana Okafor

## Slide 2: Executive Status: On Track
Overall status is GREEN; schedule variance is +4 days
Fleet-controller cutover completed for 31 of 46 pilot sites
Data migration dry run finished with 0 blocking defects
  Two medium defects in telemetry backfill, fixes in review
Risk: certification lab availability in September (mitigation booked with second lab in Denver)
Budget consumed: $3.42M of $5.10M approved (67%)

## Slide 3: Key Metrics vs. Plan
Metric | Plan (Jul) | Actual (Jul) | Variance
Sites cut over | 28 | 31 | +3
Open defects (sev 1-2) | 0 | 0 | 0
Open defects (sev 3) | 12 | 9 | -3
Fleet uptime during cutover | 99.50% | 99.74% | +0.24 pt
Migration cost per site ($K) | 74.0 | 69.8 | -4.2
Trained site operators | 180 | 196 | +16

## Slide 4: Delivery Timeline
Phase 1
Platform build
Jan - Apr 2026
complete
Phase 2
Pilot cutovers
May - Aug 2026
in progress
Phase 3
Fleet rollout
Sep - Dec 2026
Phase 4
Decommission 3.x
Jan - Feb 2027
complete / in progress
not started

## Slide 5: Summary and Asks
Project remains on schedule and 4% under budget
Pilot exit review scheduled for 21 August 2026
Ask: approve $180K contingency for second certification lab
Ask: confirm freeze window for the September fleet rollout
Next report: 29 August 2026